## Project Backlog
ID | Title | As a/an | I want to… | so that… | Confirmations | Notes | Priority | Status /name/blank /done/accepted | Time Estimate | Actual Time
9 | Mobile friendly | teacher | have my website available and easy to use on a mobile phone or tablet | customers can have a positive experience on their mobile devices |  |  | 0 |  | 10
1 | Home page | potential student | view the teachers web page | I can assess if I am interested in taking music lessons from this teacher |  |  | 1 | Done | 2 | 2
2 | Studio map | potential student | see a map of the teachers studio | I know if it is close to my house, bus routes, etc. |  |  | 2 | Done | 2 | 0.5
3 | Lesson Costs | potential student | see lesson costs |  |  |  | 3 | Done | 1 | 1
5 | Teacher bio | potential student | view a short bio of the teacher | I know if their personality, experience, and expectations match mine |  |  | 4 | Done | 1 | 0.5
4 | About page | potential student | view a photo of the teacher |  |  |  | 5 |  | 2
7 | Teaching schedule | potential student | see the teachers schedule | I know if the teacher has availability at times that are convenient for me to take lessons |  |  | 6 | Done | 4 | 1 | 22 | hours
6 | Contact form | potential student | be able to easily contact the teacher | I can ask questions before deciding if I want to take lessons from them |  |  | 7 |  | 4
8 | Twitter feed | teacher | have my Twitter feed available on my home page | I can share relevant news and information with my students and potential students that may not have Twitter. |  |  | 8 | Done | 1 | 0.5
12 | See all students | teacher | see a list of all my students & their details |  |  |  | 9 |  | 8
10 | Add student | teacher | add a new student to my records |  |  |  | 10 |  | 6
11 | Delete student | teacher | delete student(s) from my records |  |  |  | 11 |  | 2 |  | 21 | hours
13 | Update student | teacher | update student records |  |  |  | 12 |  | 8
14 | Search students | teacher | search for students by first name, last name, or phone number |  |  |  | 13 |  | 8 |  | 16 | hours
| http://www.mountaingoatsoftware.com/blog/a-sample-format-for-a-spreadsheet-based-product-backlog | [6 empty] | Actual Hours of Work | 59 | 5.5
[7 empty] | Hours of work (including 70% velocity) that can be completed by a 4 person team in 1 iteration (1 week) working 10 hours / iteration: | 28
[7 empty] | Hours of work (including 70% velocity) that can be completed by a 3 person team in 1 iteration (1 week) working 10 hours / iteration: | 21
Iteration 3
Iteration 2
Iteration 1

## User Stories
ID | Title | As a/an | I want to… | so that… | Priority | Time Estimate
1 | Home page | potential student | view the teachers web page | I can assess if I am interested in taking music lessons from this teacher | 1 | 2
2 | Studio map | potential student | see a map of the teachers studio | I know if it is close to my house, bus routes, etc. | 2 | 2
3 | Lesson Costs | potential student | see lesson costs |  | 3 | 1
4 | About page | potential student | view a photo of the teacher |  | 5 | 2
5 | Teacher bio | potential student | view a short bio of the teacher | I know if their personality, experience, and expectations match mine | 4 | 1
6 | Contact form | potential student | be able to easily contact the teacher | I can ask questions before deciding if I want to take lessons from them | 7 | 4
7 | Teaching schedule | potential student | see the teachers schedule | I know if the teacher has availability at times that are convenient for me to take lessons | 6 | 4
8 | Twitter feed | teacher | have my Twitter feed available on my home page | I can share relevant news and information with my students and potential students that may not have Twitter. | 8 | 1
9 | Mobile friendly | teacher | have my website available and easy to use on a mobile phone or tablet | customers can have a positive experience on their mobile devices | 0 | 10
10 | Add student | teacher | add a new student to my records |  | 10 | 6
11 | Delete student | teacher | delete student(s) from my records |  | 11 | 2
12 | See all students | teacher | see a list of all my students & their details |  | 9 | 8
13 | Update student | teacher | update student records |  | 12 | 8
14 | Search students | teacher | search for students by first name, last name, or phone number |  | 13 | 8
[5 empty] | Actual Hours of Work | 59
|  |  |  | Hours of work (including 70% velocity) that can be completed by a 4 person team in 1 iteration (1 week) working 10 hours / iteration: | 28
|  |  |  | Hours of work (including 70% velocity) that can be completed by a 3 person team in 1 iteration (1 week) working 10 hours / iteration: | 21